## Sheet1
Description | Assesment | Likelihood | Impact | Responsibility | Implemented | Proposed | Response
Database is comprimised | stolen or changed data within database whilst public | low | high | Sam Jones | use encrypted date wherever possible | none | create new VM
VM stops working | app wont function | low | high | GCP | Repository | none | create new VM
Jenkins doesnt function correctly | testing doesnt function | low | low | Sam Jones | none | none | reploy jenkins VM
Web server doesnt respond | web app wont function | low | low | GCP | none | none | create new VM
potential sensitive information public on Github | could give any user access to any information | low | medium | Github | none | none | use environment varaibles to safeguard public information